## Dashboard
Project Management Dashboard Template |  |  |  |  | Jan D, YYYY — Jan D, YYYY | [5 empty] | 2024-12-19
Start date: | 2024-01-01 |  | Project manager: |  | Peter Maxwell | [8 empty] | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15
Project | Tasks | Priority | Department | Assignee | Manager | Status | Start date | Duration | Due date | Days left | Progress | Budget | Actual cost | bar: 2024-12-19 to 2025-01-15
Compliance | Task8 | Low | Development | Davina B. | Kevin J. | In Progress | 2024-11-30 | 20 | 2024-12-31 | 7 | 30% | 16000 | 16200
Digitalisierung | Task7 | Medium | Development | Davina B. | Kevin J. | Overdue | 2024-01-28 | 20 | 2024-02-23 | -214 | 50% | 6000 | 6600
Infrastruktur | MPS L7 | High | Security | Samantha F. | Sasha H. | Overdue | 2024-02-14 | 10 | 2024-02-27 | -212 | 5% | 5000 | 4500
Kultur | Line 1 | Critical! | Marketing | Jenna A. | Prudence P. | On Hold | 2024-02-27 | 30 | 2024-04-08 | -183 | 30% | 1000 | 1001
Organisationsstruktur | Lean Administaration | Medium | MPS | Max Mustermann | Kevin J. | In Progress | 2024-01-11 | 3 | 2024-01-15 | -243 | 65% | 1000 | 999
Personal / Know - how | Lean Line 7 | Medium | Marketing | Tom D. | Prudence P. | In Progress | 2024-01-06 | 50 | 2024-03-15 | -199 | 95% | 1000 | 1000
Prozesse & Effiziens | mps L1 | Medium | Design | George H. | Jason B. | On Hold | 2024-02-02 | 10 | 2024-02-15 | -220 | 15% | 23000 | 12000
Stakeholder | Task6 | High | Content | David E. | Helen C. | Complete | 2024-02-20 | 65 | 2024-05-20 | - | 100% | 43000 | 40000
Meilenstein | Meilenstein Kick Off | Critical! | (Leer) | (Leer) | (Leer) | (Leer) | 2025-01-01 | 1 | 2025-01-01 | 8
Gesamtergebnis | [10 empty] | 48.75% | 96000 | 82300
86%
Go to Project
11%
Settings
Help
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Table
Project Management Template With Dashboard
Project manager |  | Peter Maxwell | Client |  | Project summary
Project start date |  | 2024-01-01 | Sponsor |  | The goal of this project is to…
Project end date |  |  | Total budget
Project | ! | Tasks | Priority | Description | Department | Assignee | Manager | Status | Progress | Start date | Duration | Due date | Days left | Budget | Actual cost | Notes
Organisationsstruktur | r | Lean Administaration | Medium | Einführen von Lean Adm | MPS | Max Mustermann | Kevin J. | In Progress | 65% | 2024-01-11 | 3 | 2024-01-15 | -243 | 1000 | 999
Personal / Know - how | r | Lean Line 7 | Medium |  | Marketing | Tom D. | Prudence P. | In Progress | 95% | 2024-01-06 | 50 | 2024-03-15 | -199 | 1000 | 1000
Kultur | r | Line 1 | Critical! |  | Marketing | Jenna A. | Prudence P. | On Hold | 30% | 2024-02-27 | 30 | 2024-04-08 | -183 | 1000 | 1001
Infrastruktur | r | MPS L7 | High |  | Security | Samantha F. | Sasha H. | Overdue | 5% | 2024-02-14 | 10 | 2024-02-27 | -212 | 5000 | 4500
Prozesse & Effiziens | r | mps L1 | Medium |  | Design | George H. | Jason B. | On Hold | 15% | 2024-02-02 | 10 | 2024-02-15 | -220 | 23000 | 12000
Stakeholder | a | Task6 | High |  | Content | David E. | Helen C. | Complete | 100% | 2024-02-20 | 65 | 2024-05-20 | - | 43000 | 40000
Digitalisierung | r | Task7 | Medium |  | Development | Davina B. | Kevin J. | Overdue | 50% | 2024-01-28 | 20 | 2024-02-23 | -214 | 6000 | 6600
Compliance |  | Task8 | Low |  | Development | Davina B. | Kevin J. | In Progress | 30% | 2024-11-30 | 20 | 2024-12-31 | 7 | 16000 | 16200
Meilenstein |  | Meilenstein Kick Off | Critical! | [6 empty] | 2025-01-01 | 1 | 2025-01-01 | 8
Formulas:
Due date = IF(AND(ProjectTable[[#This Row],[Start date]]<>"",[Duration]<>""),WORKDAY.INTL(ProjectTable[[#This Row],[Start date]]-1,[Duration],1,Settings!$G4:G52),"")
Days left = IF(OR('Project Table'!$[Status]="Complete",ProjectTable[[#This Row],[Due date]]=""),"-",NETWORKDAYS.INTL(TODAY(),'Project Table'!$[Due date],1,Settings!$G4:G42))
Dashboard
Settings
Help
Note on E6: To change the values in the dropdown list, go to the next sheet and simply replace a value with a custom one in the "Priority dropdown" column. Example: You wish to replace the value "Medium" in the dropdown list to "Unknown". Step1: Click on "Sheet2" at the bottom left of the screen. Step2: In the "Priority dropdown" column, locate the cell that says "Medium". Step3: Delete "Medium" and replace it with "Unknown" (or any other value of your choosing). You can use the same method to replace the values in the dropdown list of the "Status" column.
Note on K6: You can choose the percentage via the dropdown list, or you can type in a custom number. Note: The bar will not automatically change to "100%" if the status is changed to "Complete".

## Settings
Settings
⬇️FIELDS FOR THE DROPDOWN SELECTION - PROJECT TABLE -
[5 empty] | Holidays | Today's date: | 2024-12-19
Priority dropdown | Status dropdown | Department | Assignee | Manager | 2024-12-25 | Show "i" notification | 4 | days before the deadline
High | In Progress | TEST | Max Mustermann |  | 2024-07-04
Medium | Complete | TEST 1 | Franz Franzmann |  | 2024-12-24
Low | In Review | TEST 2 | Hans Hansen |  | 2024-01-01
Critical! | On Hold | TEST 3 |  |  | 2025-05-01
Blocked
Overdue
Not started
Die Ferien in Niedersachsen für das Jahr 2025 sind12:
Halbjahresferien: 3. - 4. Februar
Osterferien: 7. - 19. April (plus 30. April als Brückentag)
Pfingstferien: 2. Mai, 30. Mai und 10. Juni (als Feiertage)
Sommerferien: 3. Juli - 13. August
Herbstferien: 13. - 25. Oktober
Weihnachtsferien: 22. Dezember - 5. Januar
Go to Dashboard
Go to Project
Help

## Formulae for the dashboard
Status dropdown |  |  | Actual cost | Budget |  |  | % Duration of project |  |  | Remaining % of project
|  | Bar chart | 82300 | 96000 | Scroll bar: | 353 | Project | Tasks | Status | Number of tasks total | 9
In Progress | 3 | Doughnut | 85.73% | 14.27% |  |  | Organisationsstruktur | Lean Administaration | In Progress | Number of "Complete" tasks | 1 | Today's date: | 2024-12-19
Complete | 1 | [5 empty] | Personal / Know - how | Lean Line 7 | In Progress | Number of remaining tasks | 8
In Review | 0 | [5 empty] | Kultur | Line 1 | On Hold
On Hold | 2 | [5 empty] | Infrastruktur | MPS L7 | Overdue | Complete | 11.11%
Blocked | 0 | [5 empty] | Prozesse & Effiziens | mps L1 | On Hold | Remaining | 88.89%
Overdue | 2 | [5 empty] | Stakeholder | Task6 | Complete
Not started | 0 | [5 empty] | Digitalisierung | Task7 | Overdue
[7 empty] | Compliance | Task8 | In Progress
[7 empty] | Meilenstein | Meilenstein Kick Off | (Leer)
Remaining tasks | 7 | [5 empty] | Gesamtergebnis
Total tasks | 8
Complete | 12.5%
Remaining | 87.5%
Priority dropdown
High | 13
Medium | 0
Low | 10
Critical! | 2