## Schedule
Construction execution schedule | [50 empty] | [42]
 | time axis 2024-01-01 to 2028-12-01
|  |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
TASK DESCRIPTION | PLAN START | PLAN END | TYPE | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
|  |  |  | 1 | 5 | 9 | 14 | 18 | 22 | 27 | 31 | 35 | 40 | 44 | 48 | 1 | 5 | 9 | 14 | 18 | 22 | 27 | 31 | 36 | 40 | 44 | 49 | 1 | 5 | 9 | 14 | 18 | 23 | 27 | 31 | 36 | 40 | 44 | 49 | 1 | 6 | 10 | 14 | 18 | 23 | 27 | 31 | 36 | 40 | 45 | 49 | 1 | 6 | 10 | 14 | 19 | 23 | 27 | 32 | 36 | 40 | 45 | 49
Tender Phase | 2024-12-12 | 2025-04-15 | O
Contract signing | 2025-04-14 | 2025-04-18 | O
MTO / BOQ for purchasing | 2025-04-21 | 2025-04-21 | B
Handover of isometrics | 2025-05-05 | 2025-06-16 | B
Receiving all informations for caclculation of secondary supports | 2025-04-21 | 2025-04-25 | B
Calculation and design of secondary supports | 2025-05-01 | 2025-09-15 | O
Start purchasing supports | 2025-06-15 | 2025-10-15 | O
Material purchase and receiving (100%) | 2025-05-01 | 2025-09-15 | O
Prefabrication | 2025-06-23 | 2025-12-13 | O
Erection commencement day | 2025-06-30 | 2025-06-30 | O
Site mobilization | 2025-07-14 | 2025-07-26 | O
Start erection | 2025-08-04 | 2026-06-04 | O
Insert new rows ABOVE this one
Construction Schedule Template © 2017 Vertex42.com
Note on D6: TYPE: This column is set up to allow you to change the colors of the bar charts. Default (blank) = Gray B = Blue G = Green R = Red Y = Yellow O = Orange P = Purple X = Black