## Schedule
Construction execution schedule | [50 empty] | [42]
 | time axis 2024-01-01 to 2028-12-01
|  |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
TASK DESCRIPTION | PLAN START | PLAN END | TYPE | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
|  |  |  | 1;2;3;4;5 | 5;6;7;8;9 | 9;10;11;12;13 | 14;15;16;17;18 | 18;19;20;21;22 | 22;23;24;25;26 | 27;28;29;30;31 | 31;32;33;34;35 | 35;36;37;38;39;40 | 40;41;42;43;44 | 44;45;46;47;48 | 48;49;50;51;52;53 | 1;2;3;4;5 | 5;6;7;8;9 | 9;10;11;12;13;14 | 14;15;16;17;18 | 18;19;20;21;22 | 22;23;24;25;26;27 | 27;28;29;30;31 | 31;32;33;34;35 | 36;37;38;39;40 | 40;41;42;43;44 | 44;45;46;47;48 | 49;50;51;52;53 | 1;2;3;4;5 | 5;6;7;8;9 | 9;10;11;12;13;14 | 14;15;16;17;18 | 18;19;20;21;22 | 23;24;25;26;27 | 27;28;29;30;31 | 31;32;33;34;35;36 | 36;37;38;39;40 | 40;41;42;43;44 | 44;45;46;47;48;49 | 49;50;51;52;53 | 1;2;3;4;5 | 6;7;8;9 | 10;11;12;13;14 | 14;15;16;17;18 | 18;19;20;21;22;23 | 23;24;25;26;27 | 27;28;29;30;31 | 31;32;33;34;35;36 | 36;37;38;39;40 | 40;41;42;43;44 | 45;46;47;48;49 | 49;50;51;52;53 | 1;2;3;4;5;6 | 6;7;8;9;10 | 10;11;12;13;14 | 14;15;16;17;18 | 19;20;21;22;23 | 23;24;25;26;27 | 27;28;29;30;31;32 | 32;33;34;35;36 | 36;37;38;39;40 | 40;41;42;43;44;45 | 45;46;47;48;49 | 49;50;51;52;53
Tender Phase | 2024-12-12 | 2025-04-15 | O
Contract signing | 2025-04-14 | 2025-04-18 | O
MTO / BOQ for purchasing | 2025-04-21 | 2025-04-21 | B
Handover of isometrics | 2025-05-05 | 2025-06-16 | B
Receiving all informations for caclculation of secondary supports | 2025-04-21 | 2025-04-25 | B
Calculation and design of secondary supports | 2025-05-01 | 2025-09-15 | O
Start purchasing supports | 2025-06-15 | 2025-10-15 | O
Material purchase and receiving (100%) | 2025-05-01 | 2025-09-15 | O
Prefabrication | 2025-06-23 | 2025-12-13 | O
Erection commencement day | 2025-06-30 | 2025-06-30 | O
Site mobilization | 2025-07-14 | 2025-07-26 | O
Start erection | 2025-08-04 | 2026-06-04 | O
Insert new rows ABOVE this one
Construction Schedule Template © 2017 Vertex42.com
Note on D6: TYPE: This column is set up to allow you to change the colors of the bar charts. Default (blank) = Gray B = Blue G = Green R = Red Y = Yellow O = Orange P = Purple X = Black