## Tabelle1
 | time axis 2024-01-01 to 2026-12-28
|  |  |  | 2024 | [51 empty] | 2025 | [51 empty] | 2026
TASK DESCRIPTION | PLAN START | PLAN END | TYPE | Jan | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
Tender Phase | 2024-12-12 | 2025-04-15 | X
Contract signing | 2025-04-14 | 2025-04-18 | Y
MTO / BOQ for purchasing | 2025-04-21 | 2025-04-21 | O
Handover of isometrics | 2025-05-05 | 2025-06-16
Receiving all informations for caclculation of secondary supports | 2025-04-21 | 2025-04-25
Calculation and design of secondary supports | 2025-05-01 | 2025-09-15
Start purchasing supports | 2025-06-15 | 2025-10-15
Material purchase and receiving (100%) | 2025-05-01 | 2025-09-15
Prefabrication | 2025-06-23 | 2025-12-13
Erection commencement day | 2025-06-30 | 2025-06-30
Site mobilization | 2025-07-14 | 2025-07-26
Start erection | 2025-08-04 | 2026-06-04
Note on D5: TYPE: This column is set up to allow you to change the colors of the bar charts. Default (blank) = Gray B = Blue G = Green R = Red Y = Yellow O = Orange P = Purple X = Black